## I3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner | Crosscutting Concerns
1 | 04. Coach Connect | 4.01 | List Coaches | Develop database schema for storing coach data | 2023-04-01 | 2023-04-14 | Completed | Jigarkumar | CN, DF-In
2 | 04. Coach Connect | 4.01 | List Coaches | Implement system interface for inbound coach data to be stored in the database | 2023-04-01 | 2023-04-14 | Completed | Tarun/Aliaksandra | SI-In
3 | 04. Coach Connect | 4.01 | List Coaches | Create API endpoint to fetch coach data | 2023-04-01 | 2023-04-14 | Completed | Fernando | CN, DF-Out
4 | 04. Coach Connect | 4.01 | List Coaches | Integrate third-party API for retrieving coach data | 2023-04-15 | 2023-04-21 | Completed | Sriharsha/Vivek | CN
6 | 04. Coach Connect | 4.01 | List Coaches | Test API endpoint for fetching coach data | 2023-04-15 | 2023-04-21 | Completed | Nishith/Riddhi | CN, DF-In, ExHL
8 | 04. Coach Connect | 4.01 | List Coaches | Develop and execute test cases to verify the user interface for List Coaches is working as intended | 2023-04-15 | 2023-04-21 | Completed | Nishith/Riddhi
5 | 04. Coach Connect | 4.01 | List Coaches | Test database schema for storing coach data | 2023-04-15 | 2023-04-21 | Completed | Nishith/Riddhi | CN, DF-In, ExHL
7 | 04. Coach Connect | 4.01 | List Coaches | Check integration with third-party API for retrieving data | 2023-04-15 | 2023-04-21 | Completed | Sriharsha/Vivek | CN, ExHL
9 | 04. Coach Connect | 4.02 | Subscribe Coach | Create API endpoint for subscribing to a coach | 2023-04-01 | 2023-04-07 | Completed | Fernando | CN, DF-In, ExHL
10 | 04. Coach Connect | 4.02 | Subscribe Coach | Create UI for selecting a coach to subscribe to | 2023-04-01 | 2023-04-07 | Completed | Sriharsha/Vivek | CC, SI-In
12 | 04. Coach Connect | 4.02 | Subscribe Coach | Implement payment gateway integration for subscription fees | 2023-04-07 | 2023-04-21 | Completed | Tarun/Aliaksandra | CN, DF-Out, ET-Ex, ExHL
14 | 04. Coach Connect | 4.02 | Subscribe Coach | Test API endpoint for subscribing to a coach | 2023-04-15 | 2023-04-21 | Completed | Nishith/Riddhi | CN, DF-In, ExHL
15 | 04. Coach Connect | 4.02 | Subscribe Coach | Check payment gateway integration for subscription fees | 2023-04-15 | 2023-04-21 | Completed | Sriharsha/Vivek | CN, ET-Ex, ExHL
11 | 04. Coach Connect | 4.02 | Subscribe Coach | Implement search functionality for coaches | 2023-04-07 | 2023-04-21 | Completed | Tarun/Aliaksandra | CN, DF-In
13 | 04. Coach Connect | 4.02 | Subscribe Coach | Test database schema for storing coach subscription data | 2023-04-15 | 2023-04-21 | Completed | Nishith/Riddhi | CN, DF-In, ExHL
17 | 04. Coach Connect | 4.03 | Schedule Appointment | Create API endpoint to schedule an appointment | 2023-04-08 | 2023-04-14 | Completed | Fernando | CN, DF-In
19 | 04. Coach Connect | 4.03 | Schedule Appointment | Implement data validation for appointment scheduling | 2023-04-15 | 2023-04-21 | Completed | Sriharsha/Vivek | FV
21 | 04. Coach Connect | 4.03 | Schedule Appointment | Test API endpoint for scheduling an appointment | 2023-04-15 | 2023-04-21 | Completed | Nishith/Riddhi | CN, DF-In
16 | 04. Coach Connect | 4.03 | Schedule Appointment | Develop database schema for storing appointment data | 2023-04-01 | 2023-04-07 | Completed | Jigarkumar | CN, DF-In
18 | 04. Coach Connect | 4.03 | Schedule Appointment | Implement search functionality for appointment data | 2023-04-15 | 2023-04-21 | Completed | Sriharsha/Vivek | CN, DF-In
20 | 04. Coach Connect | 4.03 | Schedule Appointment | Test database schema for storing appointment data | 2023-04-15 | 2023-04-21 | Completed | Nishith/Riddhi | CN, DF-In
24 | 04. Coach Connect | 4.04 | Access Routine | Implement search functionality for coach and client data | 2023-04-15 | 2023-04-21 | Completed | Sriharsha/Vivek | CN, DF-In
22 | 04. Coach Connect | 4.04 | Access Routine | Develop database schema for storing coach and client data | 2023-04-08 | 2023-04-14 | Completed | Jigarkumar | DF-In, PT
23 | 04. Coach Connect | 4.04 | Access Routine | Create API endpoint for coach and client login | 2023-04-08 | 2023-04-14 | Completed | Fernando | DF-In, CN, SI-In
25 | 04. Coach Connect | 4.04 | Access Routine | Develop algorithm for tracking coach and client progress | 2023-04-15 | 2023-04-21 | Completed | Tarun/Aliaksandra | CC, DF-In
26 | 04. Coach Connect | 4.04 | Access Routine | Test database schema for storing coach and client data | 2023-04-11 | 2023-04-17 | Completed | Nishith/Riddhi | CN, DF-In
27 | 04. Coach Connect | 4.04 | Access Routine | Test API endpoint for coach and client login | 2023-04-11 | 2023-04-17 | Completed | Nishith/Riddhi | CN, DF-In
28 | 04. Coach Connect | 4.04 | Access Routine | Check integration with third-party authentication API | 2023-04-18 | 2023-04-21 | Completed | Sriharsha/Vivek | CN, ExHL

## I4
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner | Crosscutting Concerns
1 | 05. Dashboard | 5.01 | Display Fitness Activity
2 | 05. Dashboard | 5.01 | Display Fitness Activity
3 | 05. Dashboard | 5.01 | Display Fitness Activity
4 | 05. Dashboard | 5.01 | Display Fitness Activity
6 | 05. Dashboard | 5.01 | Display Fitness Activity
8 | 05. Dashboard | 5.01 | Display Fitness Activity
5 | 05. Dashboard | 5.01 | Display Fitness Activity
7 | 05. Dashboard | 5.01 | Display Fitness Activity
9 | 05. Dashboard | 5.02 | Display Diet Analysis
10 | 05. Dashboard | 5.02 | Display Diet Analysis
12 | 05. Dashboard | 5.02 | Display Diet Analysis
14 | 05. Dashboard | 5.02 | Display Diet Analysis
15 | 05. Dashboard | 5.02 | Display Diet Analysis
11 | 05. Dashboard | 5.02 | Display Diet Analysis
13 | 05. Dashboard | 5.02 | Display Diet Analysis
1 | 05. Dashboard | 5.01 | Display Fitness Activity | Define requirements for fitness data to be displayed on dashboard | 2023-04-28 | 2023-05-05 | In Progress | Jigarkumar | DF-In
2 | 05. Dashboard | 5.01 | Display Fitness Activity | Integrate back-end API for fetching fitness data | 2023-05-05 | 2023-05-09 | In Progress | Fernando | CN, DF-Out
3 | 05. Dashboard | 5.01 | Display Fitness Activity | Test dashboard functionality and UI | 2023-05-09 | 2023-05-12 | In Progress | Nishith/Riddhi | CN, DF-In, ExHL
4 | 05. Dashboard | 5.02 | Display Diet Analysis | Develop algorithm for analyzing diet data | 2023-04-28 | 2023-05-05 | In Progress | Jigarkumar | DF-In
5 | 05. Dashboard | 5.02 | Display Diet Analysis | Integrate third-party API for diet analysis | 2023-05-05 | 2023-05-09 | In Progress | Sriharsha/Vivek | CN, ExHL
6 | 05. Dashboard | 5.02 | Display Diet Analysis | Test algorithm for analyzing diet data | 2023-05-09 | 2023-05-12 | In Progress | Nishith/Riddhi | CN, DF-In, ExHL
7 | 05. Dashboard | 5.02 | Display Diet Analysis | Test data visualization for diet data | 2023-05-09 | 2023-05-12 | In Progress | Nishith/Riddhi | CN, DF-In, ExHL
8 | 05. Dashboard | 5.02 | Display Diet Analysis | Implement search functionality for diet data | 2023-05-05 | 2023-05-09 | In Progress | Tarun/Aliaksandra | CN, DF-In
9 | 05. Dashboard | 5.02 | Display Diet Analysis | Test integration with third-party API | 2023-05-09 | 2023-05-12 | In Progress | Sriharsha/Vivek | CN, ExHL
10 | 05. Dashboard | 5.03 | List User Goals | Develop database schema for storing user goal data | 2023-04-28 | 2023-05-05 | In Progress | Jigarkumar | CN, DF-In
11 | 05. Dashboard | 5.03 | List User Goals | Create API endpoint to fetch user goal data | 2023-04-28 | 2023-05-04 | In Progress | Fernando | CN, DF-Out
12 | 05. Dashboard | 5.03 | List User Goals | Integrate third-party API for retrieving user goal data | 2023-05-05 | 2023-05-12 | In Progress | Sriharsha/Vivek | CN
13 | 05. Dashboard | 5.03 | List User Goals | Test API endpoint for fetching user goal data | 2023-05-05 | 2023-05-12 | In Progress | Nishith/Riddhi | CN, DF-In, ExHL
14 | 05. Dashboard | 5.03 | List User Goals | Develop and execute test cases to verify the user interface for List User Goals is working as intended | 2023-05-05 | 2023-05-12 | In Progress | Nishith/Riddhi
15 | 05. Dashboard | 5.03 | List User Goals | Test database schema for storing user goal data | 2023-05-05 | 2023-05-12 | In Progress | Nishith/Riddhi | CN, DF-In, ExHL