## Road Map
Health Application
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 03/03/23 | Iteration 2 - 03/31/23 | Iteration 3 - 04/21/23 | Iteration 4 - 05/12/23
Module 01. Account Management | 01.01 Authenticate Account
01.02 Access/View Account Summary
01.03 Contact Customer Support Services
Module 02. Fitness Tracking | 02.01 List Fitness Routine | 3 |  | X
| 02.02 Track steps | 5 |  | X
| 02.03 Track Calories | 4 |  | X
| 02.04 Submit Rating | 5
Module 03. Nutrition Tracking | 03.01 List Food Nutrition | 3 | X
| 03.02 Track Food Intake | 4 | X
| 03.03 Modify Food Intake | 3 | X
| 03.04 Remove Food Intake | 3 | X
Module 04. Coach Connect | 04.01 List Coaches | 3 |  |  | X |  | Features implemented last sem
| 04.02 Subscribe Coach | 3 |  |  | X
| 04.03 Schedule Appointment | 4 |  |  | X
| 4.04 Access Routine | 3 |  |  | X
Module 05. Dashboard | 05.01 Display Fitness Activity | 4 |  |  |  | X
| 5.02 Display Diet Analysis | 5 |  |  |  | X
| 05.03 List User Goals | 3 |  |  |  | X
|  | VELOCITY: | 13 | 12 | 13 | 12

## Story Map
Epics |  | HealthApp - User Story Map
Epic 1 - Account Management |  | Epic 1 - Fitness Tracking | Epic 2 - Nutrition Tracking | Epic 3 - Coach Connect | Epic 4 - Dashboards
Epic 2 - Fitness Tracking | User Stories |  | 02.01 List Fitness Routine |  |  | Iteration 1
Epic 3 - Nutrition Tracking |  |  | 02.02 Track steps
Epic 4 - Coach Connect |  |  | 02.03 Track Calories
Epic 5 - Dashboards |  |  | 02.04 Submit Rating
|  | 03.02 Track Food Intake |  |  |  | Iteration 2
03.02 Track Food Intake
03.03 Modify Food Intake
03.04 Remove Food Intake
|  |  |  | 04.01 List Coaches |  | Iteration 3
04.02 Subscribe Coach
04.03 Schedule Appointment
04.04 Access Routine
[5 empty] | 05.01 Display Fitness Activity | Iteration 4
05.02 Display Diet Analysis
05.03 List User Goals