## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner | Crosscutting Concerns
1 | 05. Fitness Tracking | 5.01 | List Fitness Routine | Develop database schema for storing fitness routine data | 2023-03-17 | 2023-03-19 | Done | Jigarkumar | DF-In, DF-Out
2 | 05. Fitness Tracking | 5.01 | List Fitness Routine | Develop data model for tracking exercise routine | 2023-03-20 | 2023-03-21 | Done | Tarun/Aliaksandra | DF-In, DF-Out
3 | 05. Fitness Tracking | 5.01 | List Fitness Routine | Implement search functionality for fitness routine data | 2023-03-22 | 2023-03-23 | Done | Sriharsha/Vivek
4 | 05. Fitness Tracking | 5.01 | List Fitness Routine | Develop algorithm for calculating exercise routine statistics | 2023-03-24 | 2023-03-25 | Done | Tarun/Aliaksandra | PF
5 | 05. Fitness Tracking | 5.01 | List Fitness Routine | Implement data visualization for fitness routine data | 2023-03-26 | 2023-03-27 | Done | Tarun/Aliaksandra | PF
6 | 05. Fitness Tracking | 5.01 | List Fitness Routine | Develop test plans and execute tests to ensure UI functionality and design meet project requirements. | 2023-03-27 | 2023-03-31 | Done | Nishith/Riddhi
7 | 05. Fitness Tracking | 5.02 | Track Steps | Design data schema for storing step count | 2023-03-28 | 2023-03-29 | Done | Jigarkumar | DF-In, DF-Out
8 | 05. Fitness Tracking | 5.02 | Track Steps | Implement step tracking functionality | 2023-03-30 | 2023-03-31 | Done | Sriharsha/Vivek | DF-In, DF-Out
9 | 05. Fitness Tracking | 5.02 | Track Steps | Develop algorithm for calculating step count | 2023-03-31 | 2023-03-31 | Done | Tarun/Aliaksandra | PF
10 | 05. Fitness Tracking | 5.02 | Track Steps | Implement data validation for step count | 2023-03-31 | 2023-03-31 | Done | Nishith/Riddhi | FV
11 | 05. Fitness Tracking | 5.02 | Track Steps | Develop data visualization for step count | 2023-03-31 | 2023-03-31 | Done | Tarun/Aliaksandra | PF
12 | 05. Fitness Tracking | 5.02 | Track Steps | Create test designs for UI components and interactions with step tracking | 2023-03-31 | 2023-03-31 | Done | Nishith/Riddhi
13 | 05. Fitness Tracking | 5.03 | Track Calories | Develop data model for calorie tracking | 2023-03-17 | 2023-03-18 | Done | Nishith/Riddhi | DF-In, DF-Out
14 | 05. Fitness Tracking | 5.03 | Track Calories | Implement search functionality for calorie data | 2023-03-19 | 2023-03-20 | Done | Sriharsha/Vivek | FV
15 | 05. Fitness Tracking | 5.03 | Track Calories | Implement data validation for calorie data | 2023-03-21 | 2023-03-22 | Done | Sriharsha/Vivek | FV
16 | 05. Fitness Tracking | 5.03 | Track Calories | Develop algorithm for calculating calorie totals | 2023-03-23 | 2023-03-24 | Done | Tarun/Aliaksandra | PF
17 | 05. Fitness Tracking | 5.03 | Track Calories | Implement data visualization for calorie data | 2023-03-25 | 2023-03-26 | Done | Tarun/Aliaksandra | PF
18 | 05. Fitness Tracking | 5.03 | Track Calories | Test database schema for storing calorie data | 2023-03-27 | 2023-03-28 | Done | Nishith/Riddhi | FV, DF-In, DF-Out